## Summary
TIQCollect - Product Change Tracker
Field Collections Platform / branch TIQCollect-v2-2 / covers 2026-08-17 (repo extraction from the Collections monorepo) through 2026-09-08
Generated 2026-09-08 from git history and the working tree. Source of truth is the repository, not this file.
HEADLINE
Metric | Value |  |  | Note
Changes tracked | 84 |  |  | 73 commits + 11 uncommitted workstreams
Committed changes | 73 |  |  | all on TIQCollect-v2-2, pushed to origin
Uncommitted changes | 11 |  |  | 34 working-tree entries dated 2026-09-08 - NOT yet committed
Lines added | 61552 |  |  | across backend, frontend, ML and docs
Lines removed | 4080
Days elapsed | 22 |  |  | 2026-08-17 to 2026-09-08
Backend tests | 600 -> 669 |  |  | all passing, ~55s, no DB or network
Open known issues | 10 |  |  | see Open Issues sheet
Feature coverage | 6 built / 10 partial / 4 missing |  |  | against the 20-feature reference document
BY CHANGE TYPE
Type | Count
fix | 37
feature | 32
docs | 6
ml | 3
refactor | 2
security | 2
infra/ci | 1
performance | 1
BY AREA
Area | Changes
Backend / API | 47
Frontend | 31
Allocation & Routing | 19
ML & Scoring | 11
Docs | 9
Infra / CI | 4
Tests | 1
BY DATE
Date | Changes | Lines + | Lines - | Theme of the day
2026-08-18 | 5 | 1378 | 265 | Brand mark, manager performance from live data, case-detail UI
2026-08-19 | 4 | 2332 | 40 | Live agent location; allocation rules made operable and enforced
2026-08-20 | 3 | 2233 | 288 | Anomaly detection, one LLM provider seam (Groq), agent check-out
2026-08-21 | 5 | 4239 | 124 | Repayment scorecard: score, recalibrate, label, surface
2026-08-24 | 1 | 6826 | 168 | Recovery scorecard: calibration, validation, manager surface
2026-08-25 | 3 | 6955 | 62 | PTP date attribution; recovery validator on simulated outcomes
2026-08-26 | 1 | 425 | 24 | Manager endpoint scoping and month bugs; first endpoint tests
2026-08-27 | 2 | 1277 | 65 | Per-case targets; PTPs paid into the ledger
2026-08-28 | 6 | 2706 | 339 | Visit-priority ranking; number and unit consistency across screens
2026-08-31 | 6 | 2377 | 302 | Smart nightly allocation engine and beat planner shipped
2026-09-01 | 10 | 2812 | 564 | Two-stage global bipartite allocator, Empirical Bayes, manager objectives
2026-09-02 | 5 | 9549 | 223 | Collectable-money scoring, realistic EMI scale, manager metrics
2026-09-03 | 11 | 6343 | 343 | Point-in-time ML correctness, tenancy leaks, allocator magic numbers
2026-09-07 | 11 | 2803 | 662 | Six measured defect fixes, real audit-log path, CLAUDE.md rewrite
2026-09-08 | 11 | 9297 | 611 | Trained models, allocator promotion, epsilon-greedy, routing and maps
READ THIS BEFORE USING THE NUMBERS
- Line counts are git's, not a measure of value - the 8,464-line 2026-09-02 commit is mostly generated demo data.
- Everything dated 2026-09-08 is UNCOMMITTED working-tree work. It is real and tested, but it is not in any commit yet.
- All ML metrics on the Key Metrics sheet are measured on SYNTHETIC borrowers. They show the pipeline works end to end; they are not evidence about real borrowers.
- origin/main is still at 8d27a14 (2026-08-17). Every change tracked here lives on the TIQCollect-v2-2 branch.

## Change Log
Change Log - every change to TIQCollect, newest first
One row per commit since the 2026-08-17 extraction, plus the uncommitted 2026-09-08 workstreams. Detail is taken from the commit message body.
# | Date | Type | Area | Change | What changed, and why | Files | Lines + | Lines - | Status | Commit
1 | 2026-09-08 | ml | ML & Scoring | The model factory - a full scorecard development pipeline | backend/app/ml/pipeline/ (3,521 lines, 13 modules): config, preprocess, EDA, WOE/IV binning, selection (IV -> correlation -> VIF -> SFS -> sign check), train, scorecard, evaluate (KS/Gini/decile/PSI/calibration), testing, registry, serving engine, drift monitor, HTML report. Two-sided gates that FAIL rather than warn: a model is rejected for being too strong (gini_suspicious = 0.60) as readily as too weak, because this repo had already produced and reported a ROC-AUC of 1.0000 on a 40-row test set. | 13 | 3521 | 0 | Uncommitted | working tree
2 | 2026-09-08 | ml | ML & Scoring | Synthetic collections book simulator | backend/app/ml/simulation/book_simulator.py - a seeded, file-based monthly panel driven by latent willingness / capacity / reachability that are never written to the panel. No database, ~1s for 120k rows. Its difficulty is a dial: --sweep maps noise settings to achievable Gini (1.00/1.00 -> 0.531; 0.60/1.90 -> 0.322), which is the evidence that the book is calibrated rather than lucky. | 2 | 862 | 0 | Uncommitted | working tree
3 | 2026-09-08 | ml | ML & Scoring | Two trained models - recovery_risk PASS, contact_risk FAIL | First fitted artifacts in the repo (committed pickles under backend/app/ml/artifacts/). recovery_risk: WOE + logistic on 4 of 33 candidates (dpd, cibil_score, ptp_kept_ratio, overdue_amount) - out-of-time Gini 0.5149, KS 39.62, 0 rank-order breaks, gates PASS, promoted champion. contact_risk: Gini 0.190 against a 0.25 floor, gates FAIL, not promoted - and that failure is the finding: the panel is monthly (no time-of-day) and the product stores no address or phone quality. Everything is trained on SYNTHETIC borrowers; every artifact says so in its own SYNTHETIC_WARNING field. | 0 | 0 | 0 | Uncommitted | working tree
4 | 2026-09-08 | feature | ML & Scoring + Backend / API | Model serving seam, prediction log and drift monitor | services/ml_scoring_service.py (341 lines) serves the champion; models/model_prediction.py + migration b3e7d1f90c25 record every served score with its features; monitor.py compares matured outcomes against the artifact and recommends a retrain on PSI > 0.25 or a relative Gini drop > 20%. It never retrains and never promotes - promotion stays manual. GET /manager/ml/health reports what is loaded, its gate result and its out-of-time metrics whether or not scoring is on. | 4 | 532 | 0 | Uncommitted | working tree
5 | 2026-09-08 | feature | Allocation & Routing | Allocator expected-recovery term PROMOTED - +28.0% realised recovery | prob_recovery moves from clamp(shrunk_win x tier, 0.20, 0.85) to clamp(P(pay) x eb_multiplier x tier, 0.02, 0.85), paired with a rescaled value transform (knee 25,000 -> 1,000; reference log1p(12) -> log1p(20)). Measured on 1,200-case / 40-agent books at 8 unseen seeds: realised recovery +28.0% (8 of 8 seeds), recovery rate 0.2203 -> 0.2473, forecast bias +94% -> +9.5%, Brier 0.2172 -> 0.1435, value/proximity influence 0.120 -> 0.994, BLOCKED set identical throughout. Nominal objective weights UNTOUCHED - the term was not underweighted, it was unable to use the weight it had. The two ship as one change and cannot be rolled back separately; the pairing is enforced in code, not by two settings agreeing. | 3 | 427 | 0 | Uncommitted | working tree
6 | 2026-09-08 | feature | Allocation & Routing | Epsilon-greedy exploration live at 10% | ALLOCATOR_EXPLORATION_RATE = 0.10 - each night 10% of assignments go to a random ELIGIBLE agent, to produce the only unconfounded (agent, case, outcome) evidence available. Sized for ONE question - does agent identity matter at all (variance component, ~1.3 months) - not for ranking agents (~820 randomised visits EACH, out of reach at any rate). Cost measured, not assumed: +14.3% mean base-to-case distance at 10%. Two defects found while building it: epsilon meant twice what it said (a swap randomises BOTH cases), and expected_recovery_sum was accumulated before exploration ran, so the plan quietly disagreed with its own forecast. | 2 | 0 | 0 | Uncommitted | working tree
7 | 2026-09-08 | fix | Allocation & Routing | Workstream D - the planner threw away the OSRM matrix it paid for | planner_service.py called optimize_route(), took only the ordering, then recomputed distance as Haversine x 1.15 and duration as km/25 + 20 min a stop - so every ETA shown to every agent and manager was crow-flies even when OSRM answered perfectly. Also fixed: four different per-visit constants (15/20/25/30) so a day was routed against one number and reported against another; a silent Haversine fallback (now recorded as route_source); and a nightly plan that passed no time windows, handing agents stops outside RBI contact hours. Adds plan_fleet() - a real multi-vehicle CVRPTW, built and tested but deliberately NOT wired into the nightly run. | 8 | 1100 | 200 | Uncommitted | working tree
8 | 2026-09-08 | feature | Allocation & Routing | beat_reconciliation - plan vs GPS actuals | A 02:00 task (before the 03:00 retention sweep that would erase its evidence) reconstructing each completed beat's real distance from the AgentLocation trail and its real duration from visit check-in to check-out. Skips gaps over 15 minutes rather than assuming an agent teleported, ignores sub-25-metre jitter, and leaves columns NULL where there is no evidence - 'not measured' must stay distinguishable from 'measured as zero'. | 2 | 156 | 0 | Uncommitted | working tree
9 | 2026-09-08 | feature | Frontend | Workstream E - the beat map is a real map | BeatMapPage drew a decorative <svg viewBox='0 0 300 120'> laying the next eight stops on a fixed 4x2 grid: two stops 200 m apart and two 30 km apart rendered identically, so the one thing a route map exists to show was the one thing it could not. Now Leaflet - numbered stops in beat order, the OSRM road polyline, the agent's base, tap-a-stop to open the case. components/map/MapCanvas is the shared bootstrap; VITE_TILE_URL overrides the tile server. Not done, deliberately: ManagerLiveMapPage still has its own bootstrap, and manager-side drag-to-reorder route review is not built. | 6 | 369 | 45 | Uncommitted | working tree
10 | 2026-09-08 | fix | Tests | Test suite 600 -> 669 | 69 new tests across test_ml_pipeline.py (458), test_allocator_ml_shadow.py (515) and test_routing.py (297). Pins the promotion: test_old_transform_starves_the_value_term, test_promoted_transform_gives_value_influence_comparable_to_proximity, test_rescaling_does_not_hand_the_plan_to_the_largest_balances, test_blocked_set_survives_every_transform, test_promotion_settings_are_paired, test_exploration_never_sends_a_case_to_an_ineligible_agent, and test_plan_route_legs_reconcile_with_the_reported_totals. | 3 | 1270 | 0 | Uncommitted | working tree
11 | 2026-09-08 | docs | Docs | CLAUDE.md rewritten against the new tree | +455 lines. Adds 'The trained models', the allocator promotion with its measurement table, the epsilon-greedy power arithmetic and cost table, and both 2026-09-08 workstream sections. Corrects three claims VISIBLY rather than deleting them, per the repo's own convention: 'the only trained artifact is train_shadow_model.py', 'there is no AUC, Gini or accuracy figure anywhere', and the stub_main.py line. | 3 | 1060 | 366 | Uncommitted | working tree
12 | 2026-09-07 | docs | Docs | docs: track the v2 ML platform plan | 570 lines, dated 2026-09-07, superseding plan v1 (routing/allocation/maps, now folded in as workstreams D and E). Five workstreams — data foundation, an ML development factory, the models themselves, routing/OR, and OpenStreetMap — plus target metrics expressed as gates rather than hopes. Its own header says planning only, no code changed, and that is worth keeping visible: it reads like an inventory in places and is intent throughout. CLAUDE.md now says so where it lists the file. | 2 | 576 | 3 | Committed | 4d16d01
13 | 2026-09-07 | docs | Docs + Infra / CI | docs: rewrite CLAUDE.md from the tree rather than from its previous self | Every figure re-derived and every path checked. What was wrong: manager.py 31 routes / 3,756 lines / 109 db.query -> 33 / 3,967 / 114 models/ 22 files -> 21 (base.py is the declarative base, not a table) frontend lint 53 errors -> 18 changelog.md refs 35 files -> 32 line counts "~20.5k / ~17.3k" -> 20,892 / 17,863 known issues 10-12 listed as open -> all three fixed | 3 | 419 | 363 | Committed | 73a35c2
14 | 2026-09-07 | fix | Frontend | fix(frontend): four real bugs, found clearing 35 of 53 lint errors | RecordVisitPage.tsx also carries the fix that made `npm run build` work at all: `as const` plus a cast into an interface with no index signature is TS2352, and the production build had been failing on it. CI's typecheck could not see it — see the ci commit in this series. THE FOUR THAT WERE NOT COSMETIC: 1. A CONDITIONALLY-CALLED HOOK. BeatMapPage called useAnimatedValue AFTER two early returns, so on a loading render the hook was skipped and React's hook order changed between renders — state read back against the wrong slot. It shows up as a stray animation or a stale number, never as a crash. Hoisted above every return. | 11 | 293 | 110 | Committed | 8f6467f
15 | 2026-09-07 | refactor | Backend / API | refactor(dpd): one bucket rule, replacing seven copies | Two of the seven disagreed with the thresholds documented on the DPDBucket enum itself: scripts/seed_data.py no CURRENT branch (0 DPD -> BUCKET_1) workers/tasks/demo_daily_feed.py no CURRENT and no BUCKET_1 branch (5 DPD -> BUCKET_2) NO BEHAVIOUR CHANGED, and tests/test_dpd_bucket.py proves that rather than asserting it: seed_data draws DPD from a list whose minimum is 35 and demo_daily_feed from one whose minimum is 32, so the missing branches were unreachable and every value those two actually produce was already correct. The test checks each real input against the copy it replaced. | 6 | 196 | 36 | Committed | d6eff5f
16 | 2026-09-07 | fix | ML & Scoring | fix(snapshots): point case_id at the case actually being worked | score_loan set it with case_id = next((c.id for c in cases), None) over the list _load builds with NO STATUS FILTER AND NO ORDER BY. So it was whichever case Postgres happened to return first: an arbitrary one, and on a loan that has re-delinquented several times, usually a long-closed one. MEASURED on a 700-borrower synthetic book: 4,984 of 6,459 snapshots (77.2%) named a case whose last visit was a median of 130 DAYS before the snapshot's own date, with up to 9 cases per loan. Not a rare edge. | 2 | 92 | 1 | Committed | 5b60df3
17 | 2026-09-07 | fix | Allocation & Routing | fix(allocator): spec_match compared two enums that share no member | The term read spec_match = 1.0 if str(ag.specialization.value).upper() == loan_type_str.upper() else 0.5 comparing an AgentSpecialization (SECURED / UNSECURED / BOTH) against a LoanType (HOME / AUTO / PERSONAL / BUSINESS / GOLD / CREDIT_CARD / EDUCATION / MICROFINANCE). THE TWO VOCABULARIES HAVE NO MEMBER IN COMMON, so the expression was False for every pair ever scored: spec_match was the constant 0.5, the specialisation half of skills_score was inert, and the audit panel's "specialises in this loan type" reason could never fire. | 2 | 227 | 1 | Committed | 745c53c
18 | 2026-09-07 | feature | Frontend + Backend / API | feat(compliance): a real audit-log read path, replacing six invented rows | The Compliance page's "Today's Audit Log" was six rows hardcoded into the file: agent names absent from the roster, a PTP dated Jan 2025, invented case numbers, and an Export button wired to nothing — on an RBI compliance screen. The file's own author had written "Everything above and below is a fixed list written into the file." Now GET /manager/audit-log (7-day window, paginated) and /audit-log/export (CSV). Live against the demo book that is 200+ real rows where there were 6 fabricated ones. | 4 | 809 | 123 | Committed | 39b8a27
19 | 2026-09-07 | fix | Allocation & Routing + Backend / API | fix(scheduler): stop two tasks recording work they never did | ptp_reminders selected every PTP due today with reminder_sent == False, set reminder_sent = True and reminder_sent_at = now, and returned a count — under a comment reading "In production: send SMS via SMS gateway". No message was ever sent by any line of it. The flag is what made that harmful rather than merely useless. The query filters on reminder_sent == False, so marking the row REMOVED it from every future run: once "reminded", a borrower could never be reminded again, and wiring a real gateway later would have silently skipped every promise the stub had already ticked off. The column recorded a fact that never happened and then prevented the real thing from happening. | 2 | 90 | 20 | Committed | 5fa895e
20 | 2026-09-07 | infra/ci | Infra / CI | ci: run the Python the package declares, and a typecheck that can fail | Two steps that could not have passed and could not have failed. The Python pin was 3.11 against pyproject's `requires-python = ">=3.12"`, so the backend job installed an interpreter the package says it does not support. The typecheck ran `npx tsc --noEmit`, which resolves the ROOT tsconfig.json — a solution file listing project references and no files of its own. It therefore checked nothing and passed unconditionally, and it reported success for weeks while `npm run build` was failing on a type error in RecordVisitPage.tsx. A step that cannot fail is worse than no step, because it is read as evidence. `tsc -b` builds the referenced projects, which is what the build itself runs. | 1 | 13 | 2 | Committed | 0b3211c
21 | 2026-09-07 | fix | Backend / API | fix(payment): import Agent, so a colleague's case authorises instead of raising | _get_accessible_case reads Agent to check whether a colleague's case belongs to the same manager. It was used there and never imported, so that branch raised NameError instead of authorising the visit. Latent because no test exercises a same-manager colleague's case — the happy path and the forbidden path are both covered, the middle one is not. Co-Authored-By: Claude Opus 5 (1M context) <noreply@anthropic.com> | 1 | 5 | 0 | Committed | abca99f
22 | 2026-09-07 | security | Allocation & Routing | security(allocation): scope the decision export to the manager who owns the run | export_decisions_csv filtered on run_id ALONE. PlannerService is constructed with a manager_user_id and every other method uses it; this one accepted it and never read it, so any manager could export another agency's entire decision audit — case numbers, borrower-facing reasons and agent codes — by supplying a run id. | 2 | 83 | 3 | Committed | 9e3ba0b
23 | 2026-09-03 | docs | Allocation & Routing + Backend / API | docs: how tomorrow's cases actually get allocated | A reference for the nightly allocation, written from the source rather than from intent. Every figure is either a constant read out of the code or a number measured against the live database on 2026-09-03. Covers the 20:00 IST trigger, the three stages (pool filtering, the Hungarian bipartite assignment, OR-Tools route sequencing), the full objective weight table for all three manager objectives, the formula behind each of the six utility terms, and every hard gate. | 3 | 856 | 0 | Committed | 86eb6d0
24 | 2026-09-03 | fix | Frontend | fix(agent): stop the offline banner promising a queue that does not exist | AgentLayout toasted "You're offline - actions will queue" and showed "visits will sync when reconnected". There is no service worker, no manifest, no IndexedDB and no outbox anywhere in this app. A visit submitted on a dead connection was lost, and the banner was the reason an agent kept working instead of walking to find signal. A false reassurance is worse than no banner at all. Three changes, so the promise is one the app can keep. | 2 | 143 | 8 | Committed | d1bdc0a
25 | 2026-09-03 | fix | Allocation & Routing + Frontend | fix(scheduler): make a failed nightly allocation survivable and visible | The 20:00 run on 2026-09-02 was dispatched exactly on time and was dead 131 milliseconds later: [14:30:00,004] Task run_nightly_allocation received [14:30:00,135] ERROR raised unexpected: AttributeError( "type object 'AllocationOutcome' has no attribute 'DEFERRED_PTP'") No allocation_run row was written, so the only evidence was a stack trace in the worker's container logs. The manager simply found no beats the next morning with nothing to explain why. | 6 | 340 | 28 | Committed | ff2c368
26 | 2026-09-03 | security | Backend / API | security(manager): close two cross-tenant leaks in the manager API | An audit of all 31 routes in the manager router found two that read tenant data with no ownership check at all. GET /manager/visits/{visit_id}/media-urls took any visit id from any manager and returned 60-minute presigned URLs to the borrower's photograph, the agent's photograph and both call recordings. Those URLs then work with no authentication for the full hour, so the leak was not a read of someone else's row — it handed out a bearer token for another agency's biometric evidence. The check now joins through Agent and filters on manager_user_id BEFORE any URL is minted; that ordering is the fix, not an incidental detail. | 2 | 184 | 7 | Committed | c433713
27 | 2026-09-03 | fix | ML & Scoring | fix(labeller): the outcome target is what was still owed, not every cycle ever | _infer_outcome summed `case.target_amount` across every case the loan had ever had, settled ones included. A case is ONE collection cycle, so a loan accumulates them, and the bar for REPAID grew with every cycle the borrower completed: after six, it demanded 90% of six instalments inside a 30-day window. Nobody on schedule can clear that. REPAID became structurally unreachable and every positive collapsed to PARTIAL. Invisible on the demo book, where loans average 1.3 cases. The synthetic longitudinal run is the first dataset here with real cycle depth — 5.6 cases per loan — and it produced 6,619 PARTIAL against 0 REPAID out of 13,802 labelled rows. | 2 | 125 | 4 | Committed | 619e342
28 | 2026-09-03 | feature | Backend / API + Infra / CI | feat(ml): synthetic longitudinal history, to validate the pipeline end to end | The demo book cannot train a model: the oldest snapshot is 7 days old against a 30-day horizon, and no real borrower activity will arrive to mature it. The tempting shortcut — backfilling dated snapshots from today's loans — cannot be made honest, because Loan.dpd, PTP.status and Loan.last_payment_date are overwritten in place with no history. A "historical" row rebuilt from them reports a DPD that already reflects whether the borrower paid. | 7 | 1520 | 0 | Committed | cc110e8
29 | 2026-09-03 | fix | ML & Scoring + Backend / API | fix(ml): make Empirical Bayes point-in-time, and stop the trainer leaking | Three defects in the EB estimator, all of which returned a plausible number rather than failing: 1. `lookback_days` was in the signature and NOWHERE in the query. Every verified payment ever recorded was read. Every comment in this codebase describing a "180-day window" was quoting a parameter the function ignored. | 9 | 1408 | 211 | Committed | 13de28d
30 | 2026-09-03 | refactor | Backend / API + Allocation & Routing | refactor(allocator): name the magic numbers, stop double-counting agent skill | The allocator scored affinity as `base_affinity * eb_multiplier`, which multiplied two different estimators of the same quantity: a 90-day competency matrix grouped by (agent, loan_type), and an Empirical Bayes estimate over a 180-day window grouped by (agent, loan_type, DPD). Their product is not a correction — the multiplier IS the agent-versus-prior ratio, so wherever it was not 1.0 the agent's skill was counted twice. Across 468 combinations the product and the EB estimate disagreed by a median of 38%. Affinity is now the EB estimate alone, taken at its own grain. | 4 | 148 | 76 | Committed | 45e14b9
31 | 2026-09-03 | fix | Frontend | fix(cases): stop the priority badge repeating its own column header | The VISIT PRIORITY column rendered "Visit priority: Medium" under a header reading VISIT PRIORITY — the label twice, in the narrowest cell on the row. Removed via a showLabel prop rather than by deleting the prefix outright, because the badge has five call sites and only this one sits under a header. The other four are badge ROWS — the mobile case card, the agent case list, agent case detail, the beat map — where it appears beside DPD, Recovery and Status. RecoveryBadge renders High / Medium / Low from the same three words, so a bare "High" in those rows would be indistinguishable from the recovery outlook sitting next to it. Default stays true; only the table opts out. | 4 | 29 | 4 | Committed | 39e528d
32 | 2026-09-03 | fix | Frontend | fix(cases): the visited chip now means visited today | Case Management showed "✓ Visited" on 421 open cases on a day when zero had actually been visited. Every chip on the page was reporting history as if it were the morning's work, which is the opposite of what a manager scanning the list needs to know. Three faults in one line: const hasVisited = c.visit_count > 0 ¦¦ c.is_visited_today; ... isPartial ¦¦ hasVisited ? "✓ Visited" visit_count counts EVER, not today. isPartial forced the chip on its own, though a part payment is already reported by the STATUS column and by the collected figure beside it — the same fact three times. And is_visited_today, which the API computes correctly, was OR'd away to nothing. | 1 | 27 | 5 | Committed | defb059
33 | 2026-09-03 | fix | Allocation & Routing + Backend / API | fix(data): one story per case — a paid case stops, and dates say when work happened | CASE0000169 showed "Paid in Full" at 10:43 and "Partial Payment" at 14:37 on the same day, with one payment row between them and a date column reading 03 Sep for work done on 02 Sep. Three separate defects behind it. | 3 | 1563 | 0 | Committed | 73f4085
34 | 2026-09-02 | feature | Docs + Backend / API | feat(demo): put the book on a realistic EMI scale, with the tooling to undo it | A case is one collection cycle against a loan — one instalment — so it should be EMI-sized. It was not: targets ran to a median of Rs 22,333, a p95 of Rs 1.9L and a maximum of Rs 5,00,000. The targets were not the fault. target_amount is _cycle_target(overdue, emi) and sat at a median 0.80x the EMI, which is right. Loan.emi_amount was the problem — seeded with no reference to loan type, so the book carried MICROFINANCE instalments (median Rs 20,815) larger than HOME instalments (Rs 10,388), and monthly EMIs near four lakh rupees in every product. | 8 | 8464 | 0 | Committed | a84579e
35 | 2026-09-02 | fix | Frontend | fix(ui): say what the numbers mean, and make the calendar legible | Audit trail. The decisions panel rendered Object.entries(score_breakdown) verbatim, so a manager read internal key names and raw decimals — and "expected case_inn: 49631.54", a word severed by a replace("_", " ") that only ever replaced the first underscore, then clipped by a CSS truncate. But formatting was never the real problem: ten unlabelled numbers is not an explanation, because a score with no reference point says nothing about why this case went to this agent. The allocator utility is a weighted sum, so weight x score is each factor's literal share of the decision; those shares are now kept rather than discarded, ranked, and named in English. Factors that cannot move a decision by 0. ... | 5 | 406 | 118 | Committed | 9b226d6
36 | 2026-09-02 | fix | Backend / API | fix(manager): measure today against today, and stop PTPs counting settled cases | The dashboard was describing tomorrow while counting today's money. active_beats had no date filter and the loop kept each agent's LATEST beat, so the moment a plan existed for tomorrow the target, the case count and every per-agent goal came from that plan while the collections came from today. Only 142 of the two days' 214 cases overlapped, which is how the card reached "102% achieved" with agents showing more collected than they had been assigned. | 6 | 186 | 46 | Committed | 4379b89
37 | 2026-09-02 | fix | Allocation & Routing + Backend / API | fix(allocator): score on collectable money, and hold cases that should not be visited | Four defects in the allocation engine, each measured on the live book before and after. * The historical competency matrix was never read. The lookup asked ag_matrix.get(loan_type) while get_historical_competency_matrix nests the rates under "loan_type_recovery", so it ALWAYS took the fallback: a 90-day query over every payment ran nightly and was discarded, every agent scored the segment prior, and "Historical Competency Matching" was a segment average wearing an agent's name. 0/15 agents had a readable record; now 15/15. | 6 | 491 | 57 | Committed | a940aa2
38 | 2026-09-02 | feature | Backend / API | feat: sync manager dashboard metrics with real-time live visits and collections |  | 1 | 2 | 2 | Committed | 145156b
39 | 2026-09-01 | feature | Backend / API + Frontend | feat: add demo OTP auto-fill assistance and sync real-time visited stats across agent dashboard |  | 6 | 48 | 14 | Committed | d9132cf
40 | 2026-09-01 | feature | Backend / API + Frontend | feat: order blocked cases at bottom, expand audit decisions, add filter tabs and generate ML evaluation PDFs |  | 11 | 991 | 30 | Committed | 8f0374c
41 | 2026-09-01 | feature | Backend / API + Frontend | feat: implement Two-Stage Global Bipartite Allocator, Empirical Bayes ML, Manager Objectives, and Beat Resiliency |  | 19 | 1325 | 385 | Committed | 0f44f75
42 | 2026-09-01 | feature | Backend / API + Allocation & Routing | feat(planner): optimize beat clustering, exclude fully collected accounts, and fix CSV export |  | 5 | 78 | 7 | Committed | b4ad53b
43 | 2026-09-01 | fix | Frontend | fix(export): handle authenticated CSV download via blob in frontend |  | 2 | 26 | 3 | Committed | 31b703a
44 | 2026-09-01 | fix | Allocation & Routing + Backend / API | fix(planner): enforce 16km operating zone boundary to cap daily beat distance within 60-120 km |  | 3 | 57 | 15 | Committed | 51fc4e7
45 | 2026-09-01 | fix | Allocation & Routing | fix(planner): calibrate realistic expected recovery by agent competency and fix routing signature |  | 2 | 31 | 9 | Committed | 43e9617
46 | 2026-09-01 | fix | Backend / API | fix: anchor effective day queries to on or before today so future planned beats do not overwrite active dashboard |  | 4 | 13 | 11 | Committed | 6eeb48c
47 | 2026-09-01 | fix | Allocation & Routing + Frontend | fix(planner): expand beat_number column length and add toast feedback with CSV export button |  | 4 | 54 | 15 | Committed | b03d523
48 | 2026-09-01 | feature | Backend / API + Allocation & Routing | feat(compliance): make Visit Anomalies collapsible and vanish on confirm/dismiss |  | 4 | 189 | 75 | Committed | 795190e
49 | 2026-08-31 | fix | Allocation & Routing + Backend / API | fix(planner): fine-tune safety checks, database columns in export script, and SQLAlchemy query filters |  | 3 | 4 | 4 | Committed | b273362
50 | 2026-08-31 | feature | Allocation & Routing + Backend / API | feat: implement smart nightly case allocation engine, beat planner, manager API and UI preview |  | 13 | 1708 | 14 | Committed | ba92b31
51 | 2026-08-31 | docs | Docs | docs: update PLAN.md with comprehensive specification for Smart Nightly Case Allocation |  | 1 | 217 | 39 | Committed | c8b0adf
52 | 2026-08-31 | fix | Frontend | fix(frontend): remove deprecated baseUrl and ignoreDeprecations in tsconfig.app.json |  | 1 | 0 | 2 | Committed | 71e6168
53 | 2026-08-31 | performance | Backend / API + Docs | perf: optimize database indexes, compliance queries, tenancy scoping and frontend code-splitting |  | 5 | 168 | 97 | Committed | b5853b3
54 | 2026-08-31 | fix | Frontend + Backend / API | irregularity fixes |  | 12 | 280 | 146 | Committed | 6d0e794
55 | 2026-08-28 | fix | Backend / API | Group the per-agent queries the Agents page ran on every 30-second poll | A performance sweep of the whole service, measured rather than eyeballed: every main endpoint timed over HTTP and its SQL statements counted with an event listener on the live book (read-only enforced at the connection). Verdict: the read paths were already bounded — 6-18 queries per endpoint regardless of row count — with two exceptions, both the same shape and both fixed here. | 2 | 58 | 33 | Committed | 8ebc7ff
56 | 2026-08-28 | fix | Frontend | Say lakhs and crores, once, everywhere | The app had five money formatters plus seven inline copies of (n / 1000).toFixed(0) + "K". The same amount rendered differently depending on which screen you were on, and two of the five were wrong in opposite directions: bigMoney forced L on everything Rs 8,400 -> "Rs 0.1L" money forced K on everything Rs 34,18,392 -> "Rs 3418K" Neither is a unit anyone uses. Rupees are grouped and spoken in lakhs and crores, so "3418K" has to be converted in the head before it means anything, and at a glance it reads as three-point-four lakh. | 5 | 28 | 21 | Committed | 5212dbb
57 | 2026-08-28 | fix | Backend / API + ML & Scoring | Stop the visit-priority reason line contradicting the number above it | Review of the visit-priority work. Eight defects; one of them was shipping wrong text on 43% of open cases. THE REASON LINE READ POSITION OFF THE POINTS. The urgency ladder is deliberately non-monotonic — it peaks at 76-90 DPD and falls past the line — so the same points occur at BOTH ends of the range: 8 points is "under 30 days", 10 is "over 180". _reason collapsed those into one branch. The result, on live data: 12 days late -> "long past the NPA line" (not delinquent yet) 95 days late -> "mid-delinquency" (it is past the line) | 10 | 149 | 38 | Committed | 3382209
58 | 2026-08-28 | fix | Frontend | Take the fourth rupee figure and the second priority badge off the case screens | Three corrections from watching the manager case list in use, all of the same kind: a number or badge that was individually defensible and collectively confusing. | 3 | 118 | 54 | Committed | c23f5dd
59 | 2026-08-28 | fix | Frontend + Backend / API | Stop telling managers a number is "due now" | Added on 2026-08-24 as overdue_amount + penal_charges, this was arithmetically correct and still misled. The reason is position, not arithmetic: on a case row it sat a column from "Target / Collected" and was the largest number present, so it read as the amount to collect. A manager comparing "Due now Rs 15.0 L" against "Target Rs 70,000 / Collected Rs 70,000" cannot tell which figure the case is judged on. | 6 | 142 | 108 | Committed | baff9bd
60 | 2026-08-28 | feature | Backend / API + Frontend | Rank cases by what is recoverable, how urgent it is, and what has been tried | The product brief names three scores. Repayment likelihood and the recovery band were built; the third — which cases an agent should visit first — was not. Ordering came from Case.priority, computed once at case creation as dpd/90*40 + principal/500000*30 and never recomputed, so it could not see effort already spent or a recovery estimate that did not exist when the case was opened. THREE NAMED COMPONENTS, EACH SHOWN WITH ITS POINTS. A single number is not explainable, only authoritative-looking, and the brief asks for something a manager can defend to their team. | 16 | 2211 | 85 | Committed | cee1f49
61 | 2026-08-27 | feature | Backend / API | Give every case its own target, and pay the promises into the ledger | Six problems in the demo book, all of which read as bugs on the manager screens rather than as thin data. TARGETS WERE ALL THE SAME NUMBER. _cycle_target clamped at a flat CYCLE_TARGET_CAP = 70_000, and enough loans exceeded it that most cases showed an identical Rs 70,000 goal. The cap now scales with the loan's own EMI (1.5x-3.0x, ceiling Rs 5,00,000), so the figure varies with the borrower rather than with the constant. | 1 | 152 | 12 | Committed | 5d524c7
62 | 2026-08-27 | fix | Backend / API + Frontend | Fix PTP month attribution, PTP-on-payment sync, analytics KPI cards, seed uniqueness | Bug fixes only. The DPD allocation policy built alongside these has been removed; it is preserved on branch archive/dpd-allocation. | 9 | 1125 | 53 | Committed | a183102
63 | 2026-08-26 | fix | Backend / API | Fix manager endpoint scoping/month bugs; add endpoint tests | - Scope GET /manager/compliance to the current manager's agents (was counting visits and SOS agents across the whole database). - Replace 30-day-timedelta month-window loops in agents_performance() and analytics() with a shared arithmetic helper _recent_months(), which could land two iterations in one month and skip another. - Add backend/tests/test_manager_endpoints.py: first endpoint-level coverage for the /manager router (dashboard, agents, agents/performance, compliance, fraud-alerts/review) using FastAPI TestClient over an in-memory SQLite DB, incl. unit tests for _recent_months. 17 passing. | 2 | 425 | 24 | Committed | a47410d
64 | 2026-08-25 | fix | Frontend + Backend / API | Count PTPs by the date the borrower promised, not the day the row was written | PTP Conversion Rate read 0% for every month except the one the database was seeded in. The monthly aggregation bucketed on PTP.created_at, which is `server_default now()` -- a row-insert timestamp, not a business date -- so all 457 seeded PTPs carried 2026-08-21 and every other month had an empty denominator. The frontend divides by that and returns 0. | 5 | 125 | 35 | Committed | bc623dc
65 | 2026-08-25 | feature | Docs + Backend / API | Exercise the recovery validator on simulated outcomes, before the real ones exist | The cohort was scored 2026-08-24, so its outcomes do not mature until 2026-09-23, 2026-10-23 and 2026-11-22. Until then validate_recovery.py can only report "nothing admissible yet", which proves the plumbing runs but not that any metric is computed correctly. This adds a synthetic path so the whole workflow can be demonstrated and tested now. SYNTHETIC OUTCOMES ARE NEVER PRESENTED AS PRODUCTION OUTCOMES. The banner and the disclaimer are stored inside every fixture as data, not just written in a report, so the numbers cannot be separated from the warning by a copy-paste. Every verdict still ends "REPORT ONLY -- no scorecard change is authorised by this run". | 19 | 6768 | 3 | Committed | fb89b6e
66 | 2026-08-25 | feature | Frontend | Give the cases table room for a full agent name | Adding the "Due now" column to the manager cases table meant taking a unit from Agent, and grid-cols-12 had no smaller unit to give: names truncated to "Pankaj Kumar ...", which is useless when the column exists to tell a manager who is on the case. Replace the twelve equal units with proportional minmax(0,Xfr) tracks declared once and shared by the header and every row, so the two can no longer drift apart. minmax(0,...) is load-bearing — without it one long unbreakable value (a case number, a rupee figure) sets a floor wider than its share and pushes the row sideways. Agent gets 1.4fr, Case 1.05fr after a first pass still clipped DAILY20260825C01. Nothing clips now. | 2 | 62 | 24 | Committed | 1142fdf
67 | 2026-08-24 | feature | Backend / API + Docs | Add recovery scorecard calibration, validation and manager surface |  | 29 | 6826 | 168 | Committed | 674402e
68 | 2026-08-21 | feature | Backend / API | Let the repayment score reach the agent, and hide it once a case is settled | The score was computed correctly and then thrown away on the way out. The endpoint declares response_model=CaseDetailResponse, and FastAPI silently drops any key the schema does not name — no error, no log, just a missing block. Declaring RepaymentScoreItem/RepaymentFactorItem is the whole fix. The abstention shape has to survive serialisation, so it is declared explicitly: a factor with no evidence carries `abstained` and a reason and NO points. Flattening that to a contribution of zero would put a reason in front of an agent that the scorecard never gave. `is_modelled` rides along for the same reason — a hand-weighted scorecard must not be renderable as a trained model. | 2 | 59 | 0 | Committed | fec73f8
69 | 2026-08-21 | docs | Docs | docs: how to merge this repo back into the Collections platform | Records the procedure, the correct merge base, and the traps found doing it once on 2026-08-21 — including the one that silently dropped a commit by using the subtree split point as the base instead of the true common ancestor. Only the doc is committed; work in progress on schemas/agent.py and services/case_service.py is left untouched. | 1 | 88 | 0 | Committed | f812dd3
70 | 2026-08-21 | fix | Backend / API | Report collections from one source, and stop seeding money nobody verifies | Three pages showed three different collection rates for the same agent, and one endpoint disagreed with itself. GET /manager/agents/performance built its `monthly` array from AgentPerformance while its headline tiles used live payments. That table is written once a month by take_monthly_snapshot; on a seeded box its rows exist only because seed_data.py invented them (`sim_visits * random.uniform(8000, 45000)`). For agent002 the chart claimed 538 visits across six months against 127 real ones, and 102.7L collected against 6.7L actually received — a 13x gap between the chart and the tiles directly above it. | 2 | 70 | 56 | Committed | b5b1747
71 | 2026-08-21 | fix | Backend / API + ML & Scoring | Recalibrate the scorecard for a collections book, label outcomes, and show it | Three things the first real scoring run made unavoidable. 1 · Delinquency is now penalty-only (scorecard-1.1.0) v1.0.0 put the neutral point at 90 DPD — the RBI NPA line — which is right for a general lending book and wrong for this one. Every account here is already delinquent: the median is 72 DPD and 68% sits below 90, so most borrowers were being REWARDED for being merely six weeks overdue. | 11 | 657 | 13 | Committed | a5888a4
72 | 2026-08-21 | feature | Backend / API + ML & Scoring | Score how likely a borrower is to repay, and stop guessing at it | Customer.risk_score was not a score of anything. Two writers computed the same formula independently: dpd / 90 * 60 + (750 - cibil) / 750 * 40 which relabels two columns we already store. It carried no information of its own, yet fed collection_priority_score at 0.3 weight, which sets Case.priority — so a re-badged DPD was quietly ordering field work. | 16 | 3365 | 55 | Committed | 90dfa24
73 | 2026-08-20 | feature | Frontend + Backend / API | Let an agent check out, and show the street address of the next stop | Two small agent-app changes. CHECK OUT. Check-in has existed since the beginning with no counterpart: an agent went ON_DUTY and stayed there until a manager changed it from the Agents page. Since location tracking is gated on duty status, the person being tracked had no way to stop it — only their manager could. | 4 | 74 | 2 | Committed | 362737d
74 | 2026-08-20 | feature | Backend / API + Frontend | Route every AI feature through one provider seam, and run it on Groq | Six features called an LLM directly, each with its own inline client, its own hardcoded model="gpt-4o-mini", and its own `except Exception: pass`. With OPENAI_API_KEY empty every one silently served a written-in answer, and nothing anywhere recorded that it had. A missing key, an expired subscription, a rate limit and a malformed reply were indistinguishable from the outside — they all looked like the feature working normally. | 13 | 941 | 101 | Committed | e859d9a
75 | 2026-08-20 | feature | Backend / API + Frontend | Detect anomalies in field-visit evidence; take agent gender off the manager | Two changes that share endpoints/manager.py and so could not be split by file. ── 1. Visit anomaly detection ────────────────────────────────────────────── Visit has carried the evidence for this since it was written — check-in coordinates and time, per-photo GPS and capture time, a SHA-256 per image, the device id, the measured distance from the customer's address — and nothing ever read any of it. A manager's only assurance that a visit happened as reported was the geo-fence at the moment of recording, which proves where the phone was and nothing else. | 15 | 1218 | 185 | Committed | 221a9f8
76 | 2026-08-19 | feature | Frontend | Auto-fill GPS for DEMO cases on localhost so a visit can be recorded | Recording a visit is gated on the agent being within 100m of the customer's address, checked here and again server-side from the submitted coordinates. That makes the flow impossible to walk through from a desk: the demo customers sit at seeded Delhi-NCR addresses, so the form stays locked wherever you actually are. When the app is served from localhost AND the customer_ref begins with DEMO, the form now seeds its coordinates from the customer's own position whenever no fix is held or the current one is outside the fence. | 1 | 21 | 0 | Committed | 9211511
77 | 2026-08-19 | feature | Frontend + Backend / API | Make the allocation rules operable and visible to managers | The rules landed in the previous commit but could not actually function: Agent.gender existed in the database and nothing could write to it, so the female-agent requirement was correct code that could never fire. It appeared in no API response and nowhere in the frontend. | 5 | 353 | 4 | Committed | e3837b8
78 | 2026-08-19 | fix | Backend / API + ML & Scoring | Enforce customer protection rules in nightly case allocation | The allocator matched on territory and spare capacity alone, using none of the eight matching facts the schema already carries. Two of them are legal obligations rather than preferences: do_not_contact the bank has told us not to approach this customer at all, yet the case was still handed to an agent requires_female_agent could not be honoured by anything, because no agent gender was recorded anywhere in the system | 5 | 424 | 10 | Committed | acf8d62
79 | 2026-08-19 | feature | Backend / API + Frontend | Add live agent location tracking and manager map view | Backend: - New AgentLocation model + Alembic migration for a location trail table - LocationService: batch ingest of queued GPS pings, latest live positions per manager, per-day/per-agent trail with SOS-only filter - POST /agent/location batch endpoint (LocationBatchRequest/Response schemas) - GET /manager/agents/live and GET /manager/agents/{id}/trail endpoints - Nightly Celery task (3 AM IST) to prune the location trail past LOCATION_RETENTION_DAYS - New config: LOCATION_RETENTION_DAYS, LOCATION_MIN_MOVE_METRES, LOCATION_MAX_INTERVAL_SECONDS - SOS flow no longer requires lat/lon from the client; server falls back to last known fix and reports location_quality (LIVE/LAST_KNOWN/NONE), age, a ... | 22 | 1534 | 26 | Committed | af5fcdb
80 | 2026-08-18 | fix | Infra / CI | Restore voice transcription: install faster-whisper, default to local | Voice transcription was dead in both directions and had been returning HTTP 503 on every call. hosted TRANSCRIPTION_PROVIDER defaults to "openai", which needs OPENAI_API_KEY. Unset here, so _transcribe_openai raised. local Dockerfile.dev stripped the package out of the image: grep -v '^faster-whisper' requirements.txt so the fallback path would have ImportError'd anyway. The build optimisation was saving image size on a feature that consequently could not run at all. faster-whisper now installs by default; --build-arg WITH_LOCAL_STT=false restores the lighter image. | 2 | 34 | 3 | Committed | 1f7f36d
81 | 2026-08-18 | feature | Frontend | Use the TransOrg mark as the brand logo, via one component | A lucide ShieldCheck icon stood in for a logo, hand-written in five separate files — LoginPage, AgentLayout (twice), ManagerLayout and LandingPage. That is exactly how it drifted: changing the logo meant finding all five. There is now one BrandLogo. ShieldCheck is still used in RecordVisitPage, AgentCaseDetailPage and further down LandingPage, where it means "verified / RBI compliant". That is an icon, not a brand, and those stay shields. | 8 | 282 | 23 | Committed | 27f7fd8
82 | 2026-08-18 | feature | Frontend | Case detail: collection target as a meter, merged with the case chips | The Collection Target progress bar and the badge row below it were two stacked full-width rows saying related things, which split "how far along" from the context that explains it (bucket, priority, SLA) across two glances. Now one card: meter on the left, chips on the right. The ring is a METER, not a two-slice pie. The data is a single ratio against a limit, so it is one arc over a recessive track; slicing it into collected-vs-remaining would present them as peer categories to compare by area. That is also why the rupee figures stay as text rather than becoming a second segment. Geometry is copied from RankingRing on the profile page so the two agent-side rings match. | 1 | 82 | 27 | Committed | 244c64c
83 | 2026-08-18 | feature | Frontend | Field Agents: gauge + trend on collection rate, sortable columns | The Collection Rate column was a progress bar beside a percentage label — the bar encoded the number already printed next to it, so it was redundant ink. What a manager cannot get from the percentage alone is DIRECTION: a 76% that is falling and a 26% that is climbing call for opposite actions, and a bar renders them identically. | 2 | 587 | 52 | Committed | 7ce4f6b
84 | 2026-08-18 | feature | Backend / API | Compute manager performance figures from live data, not snapshots | Every per-agent figure a manager saw came from AgentPerformance, which is written by one job (take_monthly_snapshot, crontab day_of_month=1) for the month that just ENDED. The current month's row was therefore never updated while the month ran, and on a seeded database it existed only because seed_data.py created it with coll_rate = random.uniform(0.10, 0.55) * (1 + tier_mult * 0.5) list_agents then OVERWROTE the live counters with that value. One agent had 24 real visits and displayed 152; the collection rate never moved however much the agent collected. | 2 | 393 | 160 | Committed | 0d0660c

## Working Tree 2026-09-08
Uncommitted working tree - 34 entries against 86eb6d0
git status at the time of writing. Nothing below is in a commit.
Path | State | Lines + | Lines - | What it is
.gitignore | modified | 13 |  | ignore rules for generated model artifacts and datasets
CLAUDE.md | modified | 455 |  | trained models, allocator promotion, epsilon-greedy, workstreams D and E
ML-PLATFORM-PLAN.md | modified | 29 |  | plan updated against what was actually built
backend/app/api/v1/endpoints/manager.py | modified | 24 |  | GET /manager/ml/health
backend/app/core/config.py | modified | 57 |  | ML_SCORING_ENABLED, ML_MODEL_VERSION, ML_LOG_PREDICTIONS, ALLOCATOR_EXPLORATION_RATE, value-transform constants
backend/app/core/routing.py | modified | 731 |  | RouteResult with per-leg seconds/metres, OSRM /route geometry, time windows, plan_fleet CVRPTW, one visit-duration constant
backend/app/models/__init__.py | modified | 2 |  | register ModelPrediction
backend/app/models/beat.py | modified | 21 |  | route polyline, route_source, reconciled actuals
backend/app/schemas/agent.py | modified | 7 |  | beat route fields on the wire
backend/app/services/agent_service.py | modified | 9 |  | serve the stored route geometry
backend/app/services/global_allocator.py | modified | 427 |  | calibrated prob_recovery, rescaled value transform, epsilon-greedy swaps with propensity recording
backend/app/services/planner_service.py | modified | 167 |  | keep the OSRM matrix, apply contact windows, persist real per-leg figures, _ml_recovery_probabilities
backend/app/workers/celery_app.py | modified | 10 |  | beat_reconciliation at 02:00
backend/requirements.txt | modified | 42 |  | scikit-learn, scipy, joblib, ortools and the pipeline's dependencies
backend/tests/test_manager_endpoints.py | modified | 10 |  | allowlist the new ml/health route in the structural tenancy sweep
docker-compose.yml | modified | 48 |  | osrm service behind the routing profile
frontend/src/contexts/BeatContext.tsx | modified | 8 |  | carry route geometry
frontend/src/pages/agent/BeatMapPage.tsx | modified | 77 |  | decorative SVG replaced by Leaflet
frontend/src/types/index.ts | modified | 8 |  | beat route types
backend/alembic/versions/b3e7d1f90c25_add_model_predictions.py | new | 82 |  | model_predictions table
backend/alembic/versions/c8f2a41b6d09_add_beat_route_detail.py | new | 49 |  | beat route detail columns
backend/app/ml/artifacts/ | new dir |  |  | COMMITTED model bundles: model.joblib, metadata.json, scorecard.csv, eda/, evaluation/, MODEL_DEVELOPMENT.html
backend/app/ml/pipeline/ | new dir | 3521 |  | the model factory - 13 modules, config through monitor
backend/app/ml/simulation/ | new dir | 862 |  | book_simulator - seeded synthetic collections book
backend/app/models/model_prediction.py | new | 109 |  | every served score with its features
backend/app/services/ml_scoring_service.py | new | 341 |  | serves the champion behind ML_SCORING_ENABLED
backend/app/workers/tasks/beat_reconciliation.py | new | 146 |  | plan vs GPS actuals, 02:00
backend/scripts/build_modelling_dataset.py | new | 116 |  | 120k-row synthetic panel, ~2s; --sweep for the Gini table
backend/scripts/shadow_allocation_ml.py | new | 497 |  | before/after allocation on one book
backend/scripts/train_models.py | new | 107 |  | trains, gates, writes artifacts
backend/scripts/value_transform_sensitivity.py | new | 134 |  | robustness of the knee and reference constants
backend/scripts/value_transform_study.py | new | 225 |  | all five transforms, multi-seed
backend/tests/test_allocator_ml_shadow.py | new | 515 |  | pins the promotion and the exploration safety properties
backend/tests/test_ml_pipeline.py | new | 458 |  | pipeline gates, fitted bands, the two-directions invariant
backend/tests/test_routing.py | new | 297 |  | legs reconcile with totals; one visit constant
frontend/src/components/map/ | new dir | 292 |  | MapCanvas, BeatRouteMap, polyline decoder, constants

## Feature Coverage
Feature coverage - against the 20-feature AI-Powered Field Recovery Platform reference
Re-verified against the code on 2026-09-07, with the 2026-09-08 work folded into #7 and #20. 6 built / 10 partial / 4 missing.
# | Feature | Status | Where it stands
1 | AI Field-Agent Copilot | Built | /agent/cases/{id}/visit-strategy - LLM brief with a rule-based fallback, and the agent is told which one they got
2 | AI Voice to Automatic Visit Report | Partial | STT is real and hardened; the report is prose built from ALREADY-STRUCTURED fields. Nothing extracts disposition / PTP amount / date out of the speech - the agent still types all of it. core/llm.py already supports JSON-mode output, so this is one structured-output call away. Highest-value gap on the list
3 | AI Recovery Priority Score | Built | ml/visit_priority.py - recoverable value, urgency around the NPA line, effort spent. Scorecard, not a model
4 | AI Next-Best-Action Engine | Missing | No endpoint. Nothing chooses visit vs call vs reminder vs settle vs escalate
5 | Recovery-Optimized Route Planning | Partial | Assignment weights expected recovery; the planner now keeps the road matrix, applies RBI and preference time windows and persists real per-leg figures. plan_fleet (prize-collecting multi-vehicle CVRPTW) exists and is tested but is NOT wired into the nightly run
6 | Borrower 360 Profile | Built | AgentCaseDetailPage, 6 tabs. Disputes are still a visit outcome, not an object with a lifecycle
7 | AI Recovery Probability & Expected Recovery | Partial | recovery_scorecard computes rate 30/60/90 plus expected_recoverable_amount, snapshotted and surfaced - hand-weighted and uncalibrated. A TRAINED alternative now exists (recovery_risk, Gini 0.515 out-of-time) and the allocator uses it, but it is fitted on synthetic data
8 | AI Settlement Recommendation | Missing | loan.settlement_status is a read-only bank flag. No range, no policy, no approval workflow
9 | AI Agent Performance Intelligence | Built | Performance, AI insight, reallocation plan, monthly report, leaderboard, DPD and attendance breakdowns
10 | AI Fraud & Anomaly Detection | Built | fraud_service.py - 7 finding types over evidence already captured. Manager review; verdicts stored as future training labels. Rules, not a model, deliberately
11 | AI Compliance Monitor | Partial | Rules genuinely enforced (RBI hours, 100m fence, DNC, consent). No AI pattern analysis; thresholds hardcoded, not configurable
12 | Live Recovery Command Center | Partial | Map and location trail exist, and the agent beat map is now real Leaflet plus OSRM road geometry. Nothing is push-based - no WebSocket, no SSE anywhere in the tree, only polling
13 | Recovery Risk Radar | Missing | Every input already exists and is already on the wire. Pure frontend work - cheapest item on this list
14 | Digital Payment & Instant Receipt | Built | Unique receipt numbers, Razorpay UPI QR, SMS and WhatsApp receipts, borrower-OTP verification. No reconciliation workflow
15 | Offline-First Field App | Missing | The banner is honest and text drafts persist per case, but there is no service worker, no IndexedDB, no outbox. An agent still cannot complete a visit without signal
16 | Evidence & Immutable Case Timeline | Partial | Capture is thorough. The audit trail is 8 of 22 actions and there is no unified timeline view - evidence is scattered across tabs
17 | Customer Engagement Hub | Partial | Agent-triggered one-offs only. No campaigns, scheduling, PTP follow-up automation, templates or unified comms log
18 | Smart Work Queue & Gamification | Partial | The queue is real. Gamification is manager-side only - the agent cannot see their own standing
19 | Recovery Forecasting & Portfolio Analytics | Partial | Analytics are strong and all historical or current-state. No forecasting anywhere
20 | Continuous Learning & Management Insights | Partial | The loop closed on 2026-09-08 - a full development pipeline, committed artifacts, a model_predictions table and a drift monitor with retrain triggers. Still partial for one honest reason: nothing has been trained on a real outcome yet

## Open Issues
Known issues - open as of 2026-09-08
Carried from CLAUDE.md. Severity is a judgement call; everything else is verified against the tree.
# | Issue | Severity | Area | Detail
1 | Frontend lint job fails - 18 errors | Medium | Frontend / CI | All react-hooks/set-state-in-effect, down from 53 on 2026-09-06. Concentrated in the six largest pages, ManagerAnalyticsPage alone holding 7. Each is a behaviour-affecting restructure on pages with no test coverage at all. This is the only thing between CI and green
2 | No /verify-agent endpoint exists | High | Backend / Security | create_agent_verify_token mints a signed token for the QR on the agent's ID card and its own docstring describes a public /verify-agent endpoint. No such route exists anywhere in api/, so a borrower scanning the card has nothing to check it against - the anti-impersonation control is inert
3 | Audit trail mostly declared and unwritten | High | Backend / Compliance | AuditLog defines 22 action types; 8 are emitted. VISIT_RECORDED, PTP_SET, CASE_ASSIGNED, BEAT_GENERATED, DATA_EXPORT and nine others are defined and never written. Immutability is convention only - no trigger, no revoked grant
4 | Audit-log read path has a deliberate blind spot | Low | Backend / Compliance | The tenant scope is user_id IN (this manager + their agents) and IN drops NULLs, so system-written rows never appear. Correct as a default; a real gap nonetheless. The API declares it (excludes_system_rows: true). Scoping them through PTP to agent to manager is the obvious extension and is not done
5 | Two competing schema authorities | High | Backend / Infra | Eight Alembic migrations exist, but seed_data.py does drop_all plus create_all and never touches alembic_version. docker-entrypoint.sh arbitrates by checking for public.agents. Fine for a demo box; for production alembic upgrade head has to be the only path
6 | manager.py is 3,967 lines of business logic in the route layer | High | Backend / Architecture | 33 routes and 114 db.query() calls sitting directly in endpoints while a working services/ layer exists and is used by every agent flow. There is no manager_service.py. This is WHY the tenancy leaks happened: there is no single place where 'the agents this manager owns' is defined. Flagged at 2,316 lines on 2026-08-17 and 3,756 on 2026-09-06; still growing
7 | Frontend has no test tooling at all | High | Frontend | No vitest, jest, playwright or cypress. TS strict and eslint are configured, which is a good base. The six largest pages are 1.2k to 2.3k lines each
8 | Analytics have only three dimensions | Medium | Backend / Analytics | Every group_by in the manager router is agent, DPD bucket or month (plus beat date). No breakdown by branch, city or loan product - though Customer.city, Loan.loan_type and Loan.branch_code are all on the models and already populated
9 | Two rollout gates closed by default | Low | ML / Config | REPAYMENT_WRITE_RISK_SCORE=False and RECOVERY_WRITE_LABEL=False, so Loan.recovery_potential still holds random.choices() output on a seeded database. Deliberate - but it means the running system is not doing what a reader of ml/ might assume. Snapshots are written either way, and every manager surface reads the snapshot
10 | _received_within sums payments across EVERY CASE of the loan | Low | ML / Correctness | Correct and intended for the loan-level recovery scorecard. It stops being correct the moment anything asks a per-agent or per-case question. Nothing reads it that way today - recorded because the next thing that wants 'how much did this agent recover' will reach for it first, and it will look right

## Key Metrics
Measured results - the numbers behind the changes
Each of these was invisible until something measured it. Everything ML-related is measured on SYNTHETIC books; no database was reachable in this environment.
Change | Metric | Before | After | Evidence / caveat
Allocator ML promotion | Realised recovery | baseline | +28.0% (8 of 8 seeds, +18.4% to +39.6%) | 1,200-case / 40-agent books at 8 seeds the model was not trained on
Allocator ML promotion | Realised recovery rate | 0.2203 | 0.2473 | same runs
Allocator ML promotion | Forecast bias vs realised | +94% | +9.5% | same runs
Allocator ML promotion | Brier score | 0.2172 | 0.1435 (+34%, 5 of 5 seeds) | same runs
Allocator ML promotion | Value / proximity influence | 0.120 | 0.994 | the term was not underweighted; it could not use the weight it had
Allocator ML promotion | BLOCKED set | - | identical, every transform, every seed | the safety property
recovery_risk model | Out-of-time Gini | - | 0.5149 (95% CI 0.5035-0.5264) | gates PASS, promoted champion
recovery_risk model | KS | - | 39.62 | 4 of 33 candidate features selected; 0 rank-order breaks
recovery_risk model | Train vs out-of-time Gini | 0.4866 train | 0.5149 holdout | the holdout scores HIGHER - what a model that has not been overfitted looks like
contact_risk model | Out-of-time Gini | - | 0.1904 against a 0.25 floor - gates FAIL | the failure is the finding: monthly panel means no time-of-day, and the product stores no address or phone quality. A data change, not a model change
Epsilon-greedy at 10% | Mean base-to-case distance | 3.366 km | 3.847 km (+14.3%) | the real price of randomisation
Epsilon-greedy at 10% | Expected recovery forecast | 866,708 | 866,992 (+0.03%) | NOT evidence it is free - evidence the allocator cannot see agent effects at all (eb_multiplier is 1.0 in 297 of 315 cells)
Epsilon-greedy sizing | Time to answer 'does agent identity matter at all' | - | ~1.3 months at 10% | ranking individual agents needs ~820 randomised visits EACH (24,595 total) - out of reach at any tolerable rate
spec_match fix (2026-09-07) | Assignments moved | - | 2 of 227 (0.9%) | measured by loading the pre-fix file out of git show HEAD:. Expected recovery -0.80%, BLOCKED identical 15 of 15
Snapshot case_id fix | Snapshots naming the wrong case | 4,984 of 6,459 (77.2%) | 0 | median 130 days stale, up to 9 cases per loan. Existing rows are NOT corrected
DPD bucket rule | Copies of the rule | 7 | 1 | two disagreed with the enum's own comments. Reading the code found six; the test that asserts nobody restates it found the seventh
Workstream D routing | ETA source | Haversine x 1.15, km/25 + 20 min a stop | real OSRM per-leg seconds and metres | the road matrix was discarded on every beat, every night
Workstream D routing | Per-visit duration constants | 4 (15, 20, 25, 30) | 1 (routing.avg_visit_seconds) | a day was routed against one number and reported against another
Frontend lint | Errors | 53 | 18 | 35 cleared on 2026-09-07, four of which were real bugs
Backend tests | Count | 600 | 669 | all passing, ~55s, no DB or network