## Overview
TIQCollect - What We Built
Field Collections Platform - feature delivery register, 17 August to 8 September 2026
Every entry was verified against the running code, not taken from a plan document. Generated 2026-09-08.
IN ONE PARAGRAPH
In three weeks TIQCollect went from a field-visit recording app to a system that decides the work. The centrepiece is a nightly engine that allocates tomorrow's cases across the team and routes each agent's day, with every decision recorded and explainable. Around it we added the scoring that feeds it - repayment likelihood, recovery potential, visit priority, agent competency - and then, on 8 September, the first genuinely trained model, which improved simulated recovery by 28%. Alongside that: anomaly detection over visit evidence, live agent tracking, a real route map, voice-to-text visit notes, enforced RBI conduct rules, and three cross-tenant security leaks closed.
HEADLINE
| Value | Note
Features delivered | 66 | across 8 modules, 17 Aug - 8 Sep 2026
New capabilities | 51 | did not exist before this period
Existing capabilities improved | 15
Live in the product | 61 | working and switched on
Built, awaiting a release decision | 2 | fleet routing and the rejected contact model
Partially delivered | 3 | honest about what is not finished
Known gaps tracked | 16 | see the Gaps and Next sheet
Measured improvements | 12 | see the Results Measured sheet
BY MODULE
Module | Features | What it covers
Field Agent App | 13 | What the agent carries into the field
Manager Console | 13 | What the manager sees and controls
Scoring & ML | 11 | The judgement behind the decisions
Allocation Engine | 8 | Who works which case tomorrow
Platform & Security | 7 | Foundations, safety and engineering quality
Route & Beat Planning | 6 | In what order, and by which road
Compliance & Audit | 4 | Proving the rules were followed
Demo & Enablement | 4 | Showing the product credibly
THE FIVE THAT MATTER MOST
1. Smart nightly allocation, with a full audit trail
The system now decides the work. Every decision records why - the score, the rules applied, the cases blocked. Competitors sell this as a black box; we can show a regulator the reasoning.
2. A trained recovery model, driving the plan
28% more recovered on simulated books, and the plan's own forecast went from 94% optimistic to 9.5%. Switchable off in one setting.
3. Real routing, real maps, real ETAs
Road distances and times replaced straight-line guesses that had been shown to every agent and manager on every beat.
4. Visit-evidence anomaly detection
Seven kinds of suspicious pattern found in evidence already being captured, reviewed by the manager, with verdicts stored as future training data.
5. Security and compliance hardening
Three cross-tenant leaks closed with an automated check to prevent recurrence; RBI contact hours enforced in the routing itself, not just at the door.
ONE THING TO BE CLEAR ABOUT
The machine-learning results - the trained model's quality and the 28% recovery improvement - are measured on a simulated book, because no real recovery outcome has matured yet. They demonstrate that the pipeline works end to end and reports believable figures. They are not yet evidence about real borrowers. The first real 30-day outcomes mature on 23 September 2026 and 90-day outcomes on 22 November 2026, and the study should be re-run against the live book then.

## Features Delivered
Features delivered - 17 August to 8 September 2026
Filterable by module, status and date. 'New' did not exist before this period; 'Enhanced' existed and was materially improved.
# | Module | Feature | What it does | Used by | Status | New or enhanced | Delivered | Worth knowing
1 | Field Agent App | Voice note capture and automatic transcription | The agent speaks their visit notes instead of typing them. Audio is stored as evidence against the visit and transcribed to text automatically. Both agent and borrower recordings are captured and can be played back later. | Field agent | Live | Enhanced | 2026-08-18 | Runs locally by default (faster-whisper), so no per-minute cloud cost and no audio leaving the estate. Deliberately debugged against real mic audio rather than clean test files.
2 | Field Agent App | AI visit-strategy brief | Before a visit the agent gets a short brief on how to approach this borrower - what has been tried, what worked, what to avoid. If the AI is unavailable a rule-based brief is shown instead, and the agent is told which one they are reading. | Field agent | Live | Enhanced | 2026-08-20 | The honesty is the feature: an AI chip is never shown over a rule-based fallback.
3 | Field Agent App | Agent check-in and check-out at a stop | The agent marks arrival and departure at each stop, so time actually spent with a borrower is recorded rather than inferred. | Field agent | Live | New | 2026-08-20 | Feeds the 2026-09-08 beat reconciliation, which measures the real working day against the planned one.
4 | Field Agent App | Street address of the next stop | The agent sees where they are going next in words, not just a pin on a map. | Field agent | Live | New | 2026-08-20
5 | Field Agent App | Live location tracking during the working day | The agent's position is sent to the manager console through the day, building a trail of where the team actually went. | Field agent / Manager | Live | New | 2026-08-19 | Retained on a schedule and swept nightly - the trail is evidence, not permanent surveillance.
6 | Field Agent App | Ranked work queue | Cases are ordered by what is worth recovering, how urgent it is against the NPA line, and how much effort has already been spent - rather than by loan size or by list order. | Field agent | Live | New | 2026-08-28 | The reason line under each case now agrees with the score above it; previously they could contradict each other.
7 | Field Agent App | Real beat map with the road route | The agent's day is drawn on a real map: numbered stops in beat order, the actual road route between them, their base, and tap-a-stop to open the case. | Field agent | Live | New | 2026-09-08 | Replaces a decorative diagram that laid every stop on a fixed grid - two stops 200 m apart and two 30 km apart looked identical.
8 | Field Agent App | Hand-off to the phone's navigation app | One tap sends the selected stop to Google Maps for turn-by-turn directions. | Field agent | Live | Enhanced | 2026-09-08 | Kept deliberately: it is a free URL scheme, needs no API key, and the phone's own nav app is better at driving than we would be.
9 | Field Agent App | On-demand beat re-optimisation | If the day goes sideways the agent can re-order their remaining stops, respecting contact-hour windows. | Field agent | Live | Enhanced | 2026-08-31
10 | Field Agent App | Per-case target and collection meter | Each case carries its own collection target, shown as a meter on the case screen, so the agent knows what 'done' means for this borrower. | Field agent | Live | New | 2026-08-27 | Promises kept are paid into the same ledger, so the target reflects what has actually come in.
11 | Field Agent App | SOS alert and manager acknowledgement | An agent in trouble raises an SOS from the app; it surfaces on the manager console and the manager acknowledges it. | Field agent / Manager | Live | Enhanced | 2026-08-19
12 | Field Agent App | Case handover between agents | A case can be handed to a colleague with the context intact. | Field agent | Live | Enhanced | 2026-09-07 | Fixed on 2026-09-07: a missing import meant a colleague's case raised an error instead of authorising.
13 | Field Agent App | Honest offline banner and saved drafts | When signal drops the agent is told plainly what will and will not work, and their typed notes are kept per case so nothing is lost. | Field agent | Partial | New | 2026-09-03 | Deliberately honest rather than aspirational - a full offline queue does not exist yet and the banner no longer implies one.
14 | Manager Console | Live dashboard on real-time visits and collections | Today's visits, collections and agent activity update as they happen instead of showing yesterday's snapshot. | Manager | Live | Enhanced | 2026-09-02 | Also fixed: today was being measured against a different day's baseline.
15 | Manager Console | Field agent performance from live data | Collection rate, trend and ranking are computed from the live book rather than from stored monthly snapshots, with sortable columns and a gauge per agent. | Manager | Live | Enhanced | 2026-08-18
16 | Manager Console | Live agent map and location trail | Where every agent is now, and where they have been today. | Manager | Live | New | 2026-08-19 | Polling-based. Push updates (WebSocket/SSE) are not built.
17 | Manager Console | Visit-evidence anomaly review | Seven kinds of suspicious pattern are detected across evidence already captured - impossible travel between visits, overlapping visits, photo location not matching the visit, duplicate photos, very short visits, visits far from the customer, and trails that contradict themselves. The manager confirms or dismisses each. | Manager | Live | New | 2026-08-20 | Rules, not a model, deliberately. Manager verdicts are stored as labelled training data for a future model.
18 | Manager Console | AI performance narrative, insight and reallocation plan | A written performance read on each agent, a monthly report, a leaderboard, and a suggested reallocation of work - generated over the manager's own team only. | Manager | Live | Enhanced | 2026-08-20
19 | Manager Console | Allocation preview and decision audit | Before the night's plan lands, the manager can see it: which case went to which agent, the score behind it, and which cases were blocked and why. Exportable to CSV. | Manager | Live | New | 2026-08-31 | This is the differentiator against competitors who ship a black box labelled 'AI allocation'.
20 | Manager Console | Allocation rollback | A plan the manager does not accept can be rolled back. | Manager | Live | New | 2026-09-03
21 | Manager Console | Manager-operable allocation objectives | The manager sets what the allocator optimises for - recovery value, proximity, agent fit - rather than the weights being buried in code. | Manager | Live | New | 2026-09-01
22 | Manager Console | Compliance page on real data | RBI contact-hours, geofence, DNC and consent status, read from the actual audit trail. | Manager | Live | Enhanced | 2026-09-07 | Replaced six fabricated demo rows with real endpoints. The page also states plainly which control is inert (see Not Yet Built).
23 | Manager Console | Filterable case views with blocked cases ordered last | Filter tabs across the case list, and cases the rules blocked sit at the bottom rather than at the top of the queue. | Manager | Live | New | 2026-09-01
24 | Manager Console | Team attendance and DPD breakdowns | Performance split by DPD bucket and by attendance, per agent and per month. | Manager | Live | Enhanced | 2026-08-26
25 | Manager Console | Agent availability calendar | Who is available on which day, used by the nightly allocation so work is not planned for absent agents. | Manager / Field agent | Live | New | 2026-09-01
26 | Manager Console | Model health endpoint | Reports which model is loaded, whether it passed its quality gates, and its measured performance - whether or not scoring is switched on. | Manager / Ops | Live | New | 2026-09-08
27 | Allocation Engine | Smart nightly case allocation | Every night the system decides which cases each agent will work tomorrow, instead of work being handed out by hand or in rotation. | System / Manager | Live | New | 2026-08-31 | The single largest capability added in this period.
28 | Allocation Engine | Two-stage global optimiser | Rather than assigning cases one at a time, the whole day is solved at once as a single best-fit problem across every agent and every case, then checked for whether the resulting routes are actually drivable. | System | Live | New | 2026-09-01 | Cases that cannot be routed are deferred rather than silently dropped.
29 | Allocation Engine | Customer-protection hard gates | Five rules are enforced before any scoring happens: do-not-contact, hostile-borrower history, female-agent requirement, the 16 km territory limit, and promise-to-pay fatigue (three broken promises to one agent bars that agent, never the case). | System / Compliance | Live | New | 2026-08-19 | Gates run before scoring, so no score can ever override a protection rule.
30 | Allocation Engine | Agent competency model | The system learns which agent is good at which kind of work - by loan type and delinquency band - and shrinks that estimate toward the team average where evidence is thin, so a lucky week does not make someone a specialist. | System | Live | New | 2026-09-01 | Made point-in-time correct on 2026-09-03 so it cannot learn from the future.
31 | Allocation Engine | Scoring on collectable money | Allocation scores on what can realistically be recovered from a case, not on the headline outstanding, and holds back cases that should not be visited at all. | System | Live | New | 2026-09-02
32 | Allocation Engine | Calibrated recovery probability in the plan | The nightly plan now uses a trained model's probability that an account will pay, in place of a hand-set constant. Measured on eight independent test books: 28% more money recovered, and the forecast the plan publishes went from 94% optimistic to 9.5%. | System | Live | New | 2026-09-08 | Trained on synthetic borrowers. The first thing to do against a live book is re-run the study there before trusting the 28%.
33 | Allocation Engine | Controlled exploration (10% randomised assignment) | One assignment in ten goes to a random agent who is still fully eligible, so the business can eventually answer whether agent identity affects recovery at all - a question no amount of historical data can answer, because history was produced by this same allocator. | System | Live | New | 2026-09-08 | Costs +14.3% average travel distance. Sized to answer 'does agent identity matter' in ~1.3 months, NOT to rank individual agents (that needs ~820 randomised visits each). Single switch to turn off.
34 | Allocation Engine | Survivable nightly run | A failed allocation is visible and recoverable rather than leaving agents with no work in the morning. | System / Ops | Live | New | 2026-09-03
35 | Route & Beat Planning | Beat planner with real road distances | Each agent's day is sequenced into a route, and the distances and arrival times shown come from the road network rather than straight-line estimates. | System / Field agent | Live | New | 2026-09-08 | Until 2026-09-08 the road data was fetched and then thrown away - every ETA an agent or manager saw was crow-flies. This is the fix.
36 | Route & Beat Planning | Contact-hour time windows in the plan | The nightly route respects RBI contact hours and the borrower's own stated preference, so an agent is not sent to a door at a time the rules forbid. | System / Compliance | Live | New | 2026-09-08 | Windows are soft: if no route satisfies them the plan retries without, because an agent with no beat is worse than one with an imperfect beat.
37 | Route & Beat Planning | 16 km operating zone | Daily travel is capped by territory so a day's beat stays within 60-120 km rather than sprawling. | System | Live | New | 2026-09-01
38 | Route & Beat Planning | Beat reconciliation - plan versus reality | Every completed day is measured: the real distance driven, reconstructed from the GPS trail, and the real time spent, from check-in to check-out, against what was planned. | Manager / Ops | Live | New | 2026-09-08 | Where there is no evidence the figure is left blank - 'not measured' stays distinguishable from 'measured as zero'.
39 | Route & Beat Planning | Multi-vehicle fleet routing | A full fleet route optimiser: per-agent start points, capacity, shift windows, and the ability to drop a low-value stop rather than wreck the day for it. | System | Built, not enabled | New | 2026-09-08 | Built and tested but deliberately NOT wired into the nightly run - it changes which agent gets which case, which needs its own measured release.
40 | Route & Beat Planning | Route source recorded | Every beat records whether its figures came from real road data or a fallback estimate, so the two are never confused after the fact. | Ops | Live | New | 2026-09-08
41 | Scoring & ML | Repayment likelihood score | How likely this borrower is to pay, surfaced to the agent and hidden once a case is settled. | Field agent / Manager | Live | New | 2026-08-21 | Recalibrated for a collections book on the same day - a general credit scorecard reads a delinquent book badly.
42 | Scoring & ML | Recovery potential score | How much of the outstanding is likely to come back, and how fast - at 30, 60 and 90 days - plus a rupee expected-recovery figure. | Manager | Live | New | 2026-08-24 | Kept deliberately independent of the repayment score, so the pair can say 'unlikely to pay, but HIGH to recover' about a hostile borrower on a secured loan. That disagreement is the most useful thing they produce.
43 | Scoring & ML | Visit priority score | Which case an agent should work first, from recoverable value, urgency around the NPA line, and effort already spent. | Field agent | Live | New | 2026-08-28
44 | Scoring & ML | Point-in-time history spine | One frozen row per loan per day recording exactly what was known at that moment, so future models learn from what was actually visible at decision time rather than from hindsight. | System | Live | New | 2026-08-21 | This is the asset that makes trained models possible at all. Without it every model would silently cheat.
45 | Scoring & ML | Outcome labelling from the bank feed | The nightly bank file closes the loop: what was actually paid, settled, written off or recalled is attached back to the prediction that was made about it. | System | Live | New | 2026-09-03
46 | Scoring & ML | Model development pipeline | An end-to-end factory for building credit-style scorecards: data preparation, binning, statistical feature selection, training, and a full evaluation report with the industry-standard measures. | Data science | Live | New | 2026-09-08 | Quality gates FAIL rather than warn, and they are two-sided: a model is rejected for looking too good as readily as too weak, because an implausibly perfect result is nearly always a data leak.
47 | Scoring & ML | First trained recovery model | A model that predicts whether an account will make a material payment next cycle, fitted from data rather than hand-weighted. It passed every quality gate and is what the allocator now uses. | System | Live | New | 2026-09-08 | Gini 0.515 out of time - a solid, believable figure for this kind of model. Trained on SYNTHETIC borrowers: it proves the pipeline, it is not yet evidence about real customers.
48 | Scoring & ML | Contact-success model - evaluated and rejected | A model to predict whether a visit will actually find the borrower at home. It was built, measured, failed its quality floor, and was NOT deployed. | Data science | Built, not enabled | New | 2026-09-08 | Worth reporting: the failure is the finding. It cannot work until the product stores time-of-day and address/phone quality. That is a data collection decision, not a modelling one.
49 | Scoring & ML | Prediction log and drift monitor | Every score the system serves is recorded with the inputs behind it, and a monitor compares later real outcomes against what the model expected, recommending a retrain when the book moves away from what it was built on. | Data science / Ops | Live | New | 2026-09-08 | It recommends; it never retrains or promotes by itself. Promotion stays a human decision.
50 | Scoring & ML | Model scoring switch | The trained model can be switched on or off in one setting, returning the system to its previous behaviour in a single act. | Ops | Live | New | 2026-09-08
51 | Scoring & ML | Validation harness on simulated outcomes | Because real recovery outcomes take 30 to 90 days to mature, a synthetic book with known answers is used to prove the scoring machinery works before real labels exist. | Data science | Live | New | 2026-08-25 | Real 30-day labels mature 2026-09-23; 90-day labels 2026-11-22.
52 | Compliance & Audit | Full decision audit trail for allocation | Why every case landed with every agent is recorded permanently: the score breakdown, the rules evaluated, and from 2026-09-08 the randomisation details too. | Manager / Audit | Live | New | 2026-08-31 | Under RBI outsourcing expectations this is the kind of evidence a regulator asks for, and no competitor markets it.
53 | Compliance & Audit | Audit-log read path and export | Managers can read and export the audit trail for their own team, through a single shared query so the tenant boundary cannot be dropped on one path and not the other. | Manager / Audit | Partial | New | 2026-09-07 | The API declares its own known blind spot rather than hiding it: system-written rows are excluded. Only 8 of 22 defined action types are currently written (see Not Yet Built).
54 | Compliance & Audit | Enforced field conduct rules | RBI contact hours, a 100 m geofence around the recorded address, do-not-contact and consent are enforced in the product, not left to training. | System / Compliance | Live | Enhanced | 2026-08-19 | Thresholds are currently hardcoded rather than configurable per client.
55 | Compliance & Audit | Evidence integrity fix on photo capture | A photo chosen from the gallery was being stamped with the time of submission rather than the time of capture - on evidence attached to a compliance record. Now correct, along with accuracy and altitude. | Compliance | Live | New | 2026-09-07 | Found while clearing lint. It had been hidden by a type escape hatch in the frontend.
56 | Platform & Security | Single AI provider seam | Every AI feature in the product goes through one place, so the provider can be switched by a setting, failures are classified rather than swallowed, responses are cached, and usage is counted per feature. | Platform | Live | New | 2026-08-20 | Runs on Groq by default. It never raises: callers always get an answer and always know whether it came from AI.
57 | Platform & Security | Cross-tenant access closed | Three separate leaks were found and closed where one manager could read another manager's data, and a structural test now walks every manager route and fails the build on a new unscoped one. | Security | Live | New | 2026-09-03 | The test is textual - it verifies a route mentions scoping, which is how one leak in a shared service still got past it and had to be fixed by hand.
58 | Platform & Security | Hardened session and device binding | Login tokens are bound to a device, quick-login links are single use, and rate limiting is in force. | Security | Live | Enhanced | 2026-08-17 | Carried forward and protected by tests after an earlier incident with 90-day reusable tokens.
59 | Platform & Security | Performance work on the manager console | Database indexes, grouped queries and frontend code splitting - the agents page was running one query per agent on every 30-second poll. | Platform | Live | New | 2026-08-31
60 | Platform & Security | Continuous integration | Every push builds the backend, runs the full test suite, and type-checks the frontend production build. | Engineering | Partial | Enhanced | 2026-09-07 | Backend and typecheck pass. The frontend lint step still fails on 18 warnings - the only thing between CI and green.
61 | Platform & Security | Test suite grown to 669 backend tests | The behaviours that were fixed are pinned so they cannot silently come back - including every safety property of the new allocation and exploration logic. | Engineering | Live | Enhanced | 2026-09-08 | 600 tests before 2026-09-08. Frontend still has no test tooling at all.
62 | Platform & Security | Optional road-routing service | A self-hosted routing engine can be switched on for real road distances without depending on a paid maps API. | Platform / Ops | Live | New | 2026-09-08 | Opt-in. Falls back to estimates - and says so - when it is not running.
63 | Demo & Enablement | Realistic demo book | The demonstration data now reads like a real lender's book - EMI-scale amounts, one coherent story per case, dates that say when work actually happened, and a paid case that stops being worked. | Sales / Demo | Live | New | 2026-09-02 | With tooling to reset it to a known-clean baseline.
64 | Demo & Enablement | Daily demo feed and reset | The demo environment refreshes itself each morning and can be restored to its baseline on command. | Sales / Demo | Live | New | 2026-09-02
65 | Demo & Enablement | Consistent Indian currency formatting | Lakhs and crores, formatted the same way on every screen, defined in one place. | All users | Live | New | 2026-08-28 | Part of a wider clean-up that removed duplicate rupee figures and contradictory badges from the case screens.
66 | Demo & Enablement | Brand mark applied through one component | The TransOrg mark, used consistently across the product from a single component. | All users | Live | New | 2026-08-18

## Gaps and Next
What is not built, and what we know is wrong
Included deliberately. A feature list without this is a sales document, not a status report. Priority is our judgement of business impact, not effort.
Kind | Item | Priority | Where it stands | Why, and what it would take
Not built | Next-best-action engine | High | Nothing decides between visit, call, reminder, settlement or escalation for a given case - the agent and manager decide by judgement. | Needs a decision layer that does not exist yet. Depends on the contact-success model, which currently fails its quality floor.
Not built | Settlement recommendation | High | The system carries the bank's settlement flag but proposes no settlement range, applies no policy, and has no approval workflow. | Needs policy input from the business before it can be built.
Not built | Offline-first field app | High | An agent still cannot complete a visit without signal. Notes are saved per case, but there is no queue that syncs when connectivity returns. | Competitors market offline as table stakes for Indian field conditions. This is the largest functional gap against Tier 1 vendors.
Not built | Recovery risk radar | Medium | A manager-facing early-warning view of accounts about to deteriorate. | Every input already exists and is already on the wire - this is frontend work only, and the cheapest item on the list.
Partial | Voice to structured visit report | High | Speech is transcribed and a readable report is produced, but the report is assembled from fields the agent typed. Nothing pulls the outcome, promise amount or promise date out of what was said. | The AI layer already supports structured output, so this is close - highest-value gap in the product on current reading.
Partial | Push-based live command centre | Medium | The live map and dashboards refresh by polling. Nothing is pushed to the browser. | Works, but will not scale to a large floor watching a live map.
Partial | Unified case timeline | Medium | Evidence is captured thoroughly but is spread across tabs; there is no single chronological view of everything that happened to a case. | Also: only 8 of 22 defined audit actions are actually written, so the trail is thinner than the design intends.
Partial | Customer engagement | Medium | SMS and WhatsApp are sent one at a time by an agent. No campaigns, no scheduling, no templates, no automated promise follow-up, no single comms log.
Partial | Forecasting | Medium | Analytics are strong but entirely historical or current-state. Nothing projects forward. | The trained model makes a real forecast possible for the first time.
Partial | Agent-facing gamification | Low | Leaderboards and standings exist for managers; the agent cannot see their own.
Partial | Analytics dimensions | Medium | Everything breaks down by agent, delinquency bucket or month. There is no split by branch, city or loan product. | City, loan type and branch code are already on the data and already populated - this is reporting work, not data work.
Known issue | Agent ID verification is inert | High | The QR code on an agent's ID card mints a valid signed token, but there is no public page for a borrower to check it against. The anti-impersonation control does not currently work. | The compliance page states this rather than claiming the control works. Small piece of work; real exposure.
Known issue | Two database schema authorities | High | Migrations exist, but the seeding script rebuilds the schema independently of them. Fine for a demo box; must be resolved before production.
Known issue | Manager API has grown to ~4,000 lines in one file | High | Business logic sits in the routing layer rather than a service layer. This is the direct cause of the cross-tenant leaks that had to be fixed. | Refactoring work, no user-visible change, but it is the highest-value engineering debt in the codebase.
Known issue | No frontend test tooling | High | The six largest screens are 1,200-2,300 lines each with no automated tests.
Caveat | All model results are on synthetic data | High | The trained model, its measured quality and the 28% allocation improvement are all measured on a simulated book. No real outcome has matured yet. | First real 30-day labels mature 2026-09-23; 90-day labels 2026-11-22. Re-measure against the live book then.

## Results Measured
Results - measured, not estimated
Each figure below came from running the system and measuring it. Where a result is on simulated data it says so.
What was measured | Before | After | What it means
Money recovered per night (simulated book) | baseline | +28.0% | Measured across 8 independent test books after the allocator started using a trained recovery probability. Consistent - it improved in all 8.
Accuracy of the recovery forecast the plan publishes | 94% over-optimistic | 9.5% over-optimistic | The plan now roughly describes what it will actually collect. Previously it promised nearly double.
Quality of the recovery prediction | hand-set constant | Gini 0.515 | A solid, believable figure for a collections risk model. Held up on data the model had never seen; the model was not over-fitted.
Travel distance per agent per day | 3.37 km average to first case | 3.85 km (+14.3%) | The measured price of the 10% randomised assignment. This is a cost, reported deliberately alongside the benefit.
Agent and manager ETAs | straight-line estimates | real road distances and times | The road data was already being fetched and paid for, then discarded, on every beat, every night.
Allocation decisions traceable to a reason | 0 | every decision | Score breakdown, rules applied, and blocked-case reasons, all persisted and exportable.
Snapshots pointing at the correct case | 77.2% wrong | correct | Nearly 5,000 of 6,459 records named a case whose last visit was a median of 130 days earlier. Historic rows were not retro-corrected.
Cross-tenant data leaks | 3 open | 0 | Plus an automated check that fails the build if a new one is introduced.
Duplicate copies of the delinquency-bucket rule | 7 | 1 | Two of the seven disagreed with each other. This class of duplication has caused most of this codebase's worst defects.
Backend automated tests | 600 | 669 | All passing, in under a minute, with no database or network needed.
Frontend build errors | production build broken | builds cleanly | The build had been failing for weeks while the automated check reported success - the check could not fail.
Frontend code-quality warnings | 53 | 18 | The remaining 18 are the only thing keeping the build pipeline from green.